## HOME PAGE AND CREATE ACCOUNT
WHITE MART
VERSION NO:119.0.6045.160 (Official Build) (64-bit) |  |  |  | TESTED BY:NEENU AVARACHAN
VERFIED BY: RAKHI |  |  |  | DATE:24-FEBRUARY-2024
ENVIRONMENT DETAILS:OS-WINDOWS,BROWSER-CHROME |  |  |  | MODULE NAME:HOME PAGE AND CREATE ACCOUNT
TEST ID | TEST DISCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
Wh_Home_01 | Check wether the all catagories option is working while click on them | 1.Open WhiteMart.in 2.click All Catagories | www.White Mart.in | It should display the all catagories of appliances | It displayed the all catagories | Pass
Wh_Home_02 | Check wether the TV icon is working or not | 1.Open WhiteMart.in 2.click TV | www.White Mart.in | It should display the various cataogries of tv | It displayed the all catagories of TV | Pass
Wh_Home_03 | Check wether the refrigerator icon is working while click on them | 1.Open WhiteMart.in 2.click Refrigerator | www.White Mart.in | It should display the catagories of refrigerator | It displayed the two catagories of refrigerator | Pass
Wh_Home_04 | Check wether the search bar is working while entering the data | 1.Open WhiteMart.in 2.Click search bar | www.White Mart.in | It should display the details of enterd data | It displayed the result of enterd data | Pass
Wh_Home_05 | Verify the store icon | 1.Open Whitemart.in 2.Click storeicon | www.White Mart.in | It should display the details of store | It displayed the store details | Pass
Wh_Home_06 | Check wether the item can select from all cataories option | 1.Open Whitemart.in 2.Click all Catagories 3.Click item | www.White Mart.in | It should display the more options of selected item | It displayed the various types of selected item | Pass
Wh_Home_07 | Check wether the deliver to icon is working while click on them | 1.Open Whitemart.in 2.Click deliver to icon | 686610 | It should update the piccode | Udated the zipcode | Pass
Wh_Home_08 | Check wether the registration page is loading while click on the create account icon | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number | 6787645672 | It Should goes to the registration page | Opened registration page | Pass
Wh_Home_09 | Verify Mobile number | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number | 628256167 | It should display a message enter a valid number | Displaying a message enter a valid mobile number | Pass
Wh_Home_10 | Check wether the offers icon will work while click on them | 1.Open Whitemart.in 2.Click offers | www.White Mart.in | It should display the offered items | Displayed the offered items in the store | Pass
Wh_Home_11 | Check wether the change option in the sign up page is working while click on them | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account 5.Click change | www.White Mart.in | It should allow to change the number | It allowed to change the number | Pass
Wh_Home_12 | Check wether the otp field will work while entering invalid otp | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account 5.Enter OTP | 3456 | It should display an error message at the end of the account creation | It displayed an error message" invalid otp" | Pass
Wh_Home_13 | Check wether the otp field will work while entering valid otp | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account 5.Enter OTP | 7539 | It should accept the OTP | It accepted the OTP | Pass
Wh_Home_14 | Check wether the Firstname field will work while entering first name | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account 5.Enter name | Asha | It should accept the name | It accepted the name | Pass
Wh_Home_15 | Verify the Firstname field is empty or not | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account 5.Enter first name |  | It should display a message first name field is empty | It displayed a message the firstname field is empty | Pass
Wh_Home_16 | Check wether the last name field is working while entering lastname | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account 5.Enter last name | Anil | It should accept the name | It accepted the name | Pass
Wh_Home_17 | Check wether the last name field is working while an empty field | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account 5.Enter last name |  | It should display a message the last name field is empty | It displayed a message the lastname field is empty | Pass
Wh_Home_18 | Check wether the email field is working while entering the email id | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account 5.Enter email id | neenu@gmail.com | It should accept the name | It accepted the name | Pass
Wh_Home_19 | Check wether the email field is working while an empty field | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account |  | It should allow to create account | Itaccepted the empty field | Pass
Wh_Home_20 | Check wether the set password option is working while entering all the letters in lower case | 1.Open Whitemart.in 2.Click create account 3.Enter mobile number 4.Click create account 5.Entering password | aaaaaaaaaaa | It should display a message password contain minimum 1 uppercase letter | It displayed a message Password contain minium 1 uppercase letter | Pass
Wh_Home_21 | Check wether the carousel button is working while click on each dots | 1.Open whitemart.in | www.White Mart.in | It should move to the coresponding images | It displayed the respective image | pass
Wh_Home_22 | Check wether the white mart icon will redirect to the home page while entering on them | 1.Open whitemart.in | www.White Mart.in | It should redirect to the home page | It redirected to the home page | pass
Wh_Home_23 | Check wether the view all+ field of best sellers will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should goes to the best sellers page | It directed to the best sellers page | pass
Wh_Home_24 | Check wether the view all+ field of refrigerator will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should go to the refrigerators page | It redirected to the refrigerators page | pass
Wh_Home_25 | Check wether the social media icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should redirect to the social media pages | It redirected to the social media pages | pass
Wh_Home_26 | Check wether the fullHD icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should redirect to the fullHd pages | It redirected to the full HD page | pass
Wh_Home_27 | Check wether the Home Theatre System icon of Tv will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should redirect to the Home Theatre page | It redirected to the Home Theatre page | pass
Wh_Home_28 | Check wether the subscribe button will work with out entering the emailid | 1.Open whitemart.in |  | It should display a message please enter the email id | I displayed a message please enter email_id | pass
Wh_Home_29 | Check wether the customer care icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should reidirect to the mailing page | It redirected to the mailing page | pass
Wh_Home_30 | Check wether the email icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should reidirect to the gmail | It redirected to the chrome home page | pass
Wh_Home_31 | Check wether the visit store icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should display the all store details | It displayed the store details | pass
Wh_Home_32 | Check wether the about us icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should display the detail of the company | It displayed the details of company | pass
Wh_Home_33 | Check wether the cooperate page will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should display the details of board members | It displayed the details of board members | pass
Wh_Home_34 | Check wether the contact us icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should goes to the contact page | It redirected to the contact page | pass
Wh_Home_35 | Check wether the privacy policy icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should give the details of privacy policy | It displayed the details of privay policy | pass
Wh_Home_36 | Check wether telephone icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should go to the communicating option | Its still on that page | Fail
Wh_Home_37 | Check wether the mobile number link will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should go the communicating option | It does not load anything | Fail
Wh_Home_38 | Check wether the partner login option will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should display a login page | It displayed a login page | Pass
Wh_Home_39 | Check wether the franchese login icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should display a franchese login page | It displayed a 404 error message | Fail
Wh_Home_40 | Check wether the terms and conditions icon will work while click on them | 1.Open whitemart.in | www.White Mart.in | It should display the terms and condition details | It displayed the terms and condition details | Pass
Wh_Home_41 | Check wether the subscribe button will work while entering an email id | 1.Open whitemart.in | www.White Mart.in | It should gives a confirmation message subscribed | It doest not gave a confirmation message | fail
Wh_Home_42 | Check wether the subscribe button will work while entering an invalid email id | 1.Open whitemart.in | www.White Mart.in | It should gives a message invalid email id | It doest not show a invalid email id message | Fail
Wh_Home_43 | Check wether the my orders icon will work while click on them | 1.Open whitemart.in 2.Log in | 8547509737 abcefg | It should display the details of ordered items | It displayed the details of ordered items | Pass
Wh_Home_44 | Check wether the account settings icon will work while click on them | 1.Open whitemart.in 2.Log in | 8547509737 abcefg | It should display the details account holder | It displayed the details of account holder | Pass
Wh_Home_45 | Check wether the edit button will work while click on them | 1.Open whitemart.in 2.Log in | 8547509737 abcefg | It should allow to edit the details | It allowed to edit the details | Pass
Wh_Home_46 | Check wether the check box of male and female will select while click on them | 1.Open whitemart.in 2.Log in 3.Edit | 8547509737 abcefg | It can select the checkbox | It selected the check box | Pass
Wh_Home_47 | Check wether the address icon will work while click on them | 1.Open whitemart.in 2.Log in 3.Address | 8547509737 abcefg | It should allow to add addresses | It allowed to add address | Pass
Wh_Home_48 | Check wether the change password icon will work while click on them | 1.Open whitemart.in 2.Log in 3.Change password |  | It should open a page to change the password | It opened a page to change the password | Pass
Wh_Home_49 | Check wether the password will update wether the new password and confirm password were differnet | 1.Open whitemart.in 2.Log in 3.Change password | Neenu@123 Neenu@1234 | It should display a message the password should match | It displayed a message the password should match | Pass
Wh_Home_50 | Update password button will work while click on them | 1.Open whitemart.in 2.Log in 3.Change password 4.Update password | Neenu@1234 Neenu@1234 | It should display a message the password is updated successfully once we enter the password | It displayed a message the password is updated successfully | Pass
Wh_Home_51 | Check wether the sign out button will work while click on them | 1.Open whitemart.in 2.Log in |  | It should redirect to home page once we click the sign out button | It redirected to home page after click the sign out button | Pass
Wh_Home_52 | Check wether the log in button will work while click on them | 1.Open whitemart.in 2.Log in | www.White Mart.in | It should goes to the home page | It redirected to the home page | Pass
Wh_Home_53 | Check wether the login button will work while entering an invalid email id | 1.Open whitemart.in 2.Log in | neenuka@gmail.com | It should display a message the email id is invalid | It redirected to the home page | Fail
Wh_Home_54 | Check wether the account can create through an invalid email id | 1.Open whitemart.in 2.Create account | abc@gmail.com | It should display account details once we submit the account | It displayed account details | Fail
Wh_Home_55 | Check wether the my profile icon will work while click on them | 1.Open whitemart.in 2.Create account 3.Click my profile |  | It should go to the page of respective customer | It displayed customer details | Pass
Wh_Home_56 | Check wether the wishlist will work while click on them | 1.Open whitemart.in 2.Create account 3.Click wishlist |  | It should go to the wishlist page | It displayed wishlist page | Pass
Wh_Home_57 | Check wether the continue shopping button will work while click on them | 1.Open whitemart.in 2.Create account 3.Click wishlist 4.Continue shopping | www.White Mart.in | It should redirected to the home page to purchase | It redirected to home page to purchase | Pass
Wh_Home_58 | Check wether the log out button will work while click on them | 1.Open whitemart.in 2.Click log in 3.click log out | www.White Mart.in | It should log out the user page | Log out the page of respective user | Pass
Wh_Home_59 | Check wether the forgot password link will work while click on them | 1.Open whitemart.in 2.Click log in 3.Click forgot password | www.White Mart.in | It should go to the password creating page once we enter the email id | Its opened a page to reset the password | Pass
Wh_Home_60 | Check wether the forgot password link will work while entering an invalid email id | 1.Open whitemart.in 2.Click log in 3.Click forgot password | neenuka@gmail.com | It should display a message the email id is invalid | It accepted the email id | Fail
Wh_Home_61 | Check wether the send link button will work while entering an valid email id | 1.Open whitemart.in 2.Click log in 3.Click forgot password | neenuka1991@gmail.com | It should send a link to reset the password to coresponding email | It send an email to respective email id | Pass
Wh_Home_62 | Check wether the send link button will work while entering an invalid email id | 1.Open whitemart.in 2.Click log in 3.Click forgot password | neenuka@gmail.com | It should dispalay a message the email is invalid | It displayed a message the email is invalid | Pass
Wh_Home_63 | Check wether the apply button of enter pincode will work while we enter an valid pincode | 1.Open whitemart.in 2.Click deliver to icon 3.Click enter pincode | www.White Mart.in | It should accept pincode update the details | It updated the pincode | Pass
Wh_Home_64 | Check wether the apply button of enter pincode will work while we enter an invalid pincode | 1.Open whitemart.in 2.Click deliver to icon 3.Click enter pincode | www.White Mart.in | It should display a message the pincode is invalid | It accepted the pincode | Fail

## TV AND REFRIGERATOR
WHITE MART
VERSION NO:119.0.6045.160 (Official Build) (64-bit) |  |  |  | NAME : NEENU AVARACHAN
VERFIED BY: RAKHI |  |  |  | DATE:24-FEBRUARY-2024
ENVIRONMENT DETAILS:OS-WINDOWS,BROWSER-CHROME |  |  |  | MODULE NAME:TV AND REFRIGERATOR
TEST ID | TEST DISCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
Wh_TR_01 | Check wether the normal icon in the TV page will work while click on them | 1.open white mart.in | www.whitemart.in | It should display normal tvs | It displayed the details of normal Tv | Pass
Wh_TR_02 | Check wether the drop down button of price will work while click on them | 1.open white mart.in | www.whitemart.in | It should display the list of price range | It displayed the list of price range | Pass
Wh_TR_03 | Check wether the recommended dro pdown arrow of tv will work while click on them | 1.open white mart.in 2.Click Tv 3.Click Normal | www.whitemart.in | It should display the list of various catagories | It displayed the list of various catagories | Pass
Wh_TR_04 | Check wether the drop down arrow of brand will work while click on them | 1.open white mart.in 2.Click Tv 3.Click Normal 4.Click brand | www.whitemart.in | It should display various brands of tv | It displayed the list of brands | Pass
Wh_TR_05 | Check wether the check box of tv brands will work while click on them | 1.open white mart.in 2.Click Tv 3.Click Normal 4.Click brand 5.Mark Check box | www.whitemart.in | It should select and display the various brands of tv | The Check Box selected and displayed the various tv brands | Pass
Wh_TR_06 | Check wether the check box of tvs screentype will work while click on them | 1.open white mart.in 2.Click Tv 3.Click Normal 4.Click screentype 5.Mark Check box | www.whitemart.in | It should select and display the various screen type tvs | The Check Box selected and displayed the various screen type tvs | Pass
Wh_TR_07 | Check wether the check box of full hd and hd ready will work while click on them | 1.open white mart.in 2.Click Tv 3.Click Normal 4.Click HD and HD ready 5.Mark Check box | www.whitemart.in | It should select and display hd and hd ready tvs | The check box selected and displayed the hd and hd ready tvs | Pass
Wh_TR_08 | Check wether the drop down arrow of discount will work while click on them | 1.open white mart.in 2.Click Tv 3.Click Normal 4.Click discount | www.whitemart.in | It should display the various discount rates | It displayed the various discount rates | Pass
Wh_TR_09 | Check wether the radio button of discount will work while click on them | 1.open white mart.in 2.Click Tv 3.Click Normal 4.Click discount 5.Mark Check box | www.whitemart.in | It should display the various discount tvs | It displayed the various discount tvs | Pass
Wh_TR_10 | Check wether the checkbox of add to compare | 1.open white mart.in 2.Click Tv 3.Click Normal 4.Click discount 5.Mark add to compare | www.whitemart.in | It should added to the add to compare | It added to the add to compare | Pass
Wh_TR_11 | Check wether the all icon tvs will work while click on them | 1.open white mart.in 2.Click Tv 3.Click Normal 5.Mark add to compare | www.whitemart.in | It should redirect to coresponding tv category | It redirected to the coresponding tv categories | Pass
Wh_TR_12 | Check wether the clear all items link will work while click on them | 1.Open white mart.in 2.Click tv 3.Click normal 4.click compare all items | www.whitemart.in | it should clear all items from the compare list | It removed item from the compare list | Pass
Wh_TR_13 | Check wether the refrigerator icon will work while click on them | 1.Open whitemart.in 2.Click refregerator | www.whitemart.in | It should display the two catagories of refrigerator ,single door and double door | It displayed two two catagories | Pass
Wh_TR_14 | Check wether the single door icon of refrigerator will work while click on them | 1.Open whitemart.in 2.Click refregerator 3.Click single door | www.whitemart.in | It should display the single door refigerators | It displayed an error message the item are out of stock | Fail
Wh_TR_15 | Check wether the double door icon will work while click on them | 1.Open whitemart.in 2.Click refregerator 3.Click double door | www.whitemart.in | it should display the various double door refrigerators | It displayed an error message the item are out of stock | Fail
Wh_TR_16 | Check wether the side by side refrigerator icon will work while click on them | 1.Open whitemart.in 2.Click refregerator 3.Click double door 4.Click side by side | www.whitemart.in | It should display the various side by side refrigerator | It displayed various side by side refrigerators | Pass
Wh_TR_17 | Check wether the multi door refrigerator icon will work while click on them | 1.Open whitemart.in 2.Click refregerator 3.Click double door 4.Click multi door | www.whitemart.in | It should display the various multi door refrigerator | It displayed an error message the item are out of stock | Fail
Wh_TR_18 | Check wether the bottom freezor refrigerator icon will work while click on them | 1.Open whitemart.in 2.Click refregerator 3.Click double door 4.Click bottom freezor | www.whitemart.in | IT should display the various bottom freezor refrigerators | It displayed an error message the item are out of stock | Fail
Wh_TR_19 | Check wether the drop down arrow of color will work while click on them | 1.Open whitemart.in 2.Click refregerator 3.Click double door 4.Click side by side | www.whitemart.in | It should display various colors | It displayed various colors | Pass
Wh_TR_20 | Check wether the red color checkbox will work while click on them | 1.Open whitemart.in 2.Click refregerator 3.Click double door 4.Click side by side 5.Click red color | www.whitemart.in | It should display red color refrigerator | It displayed black color refrigerator | Fail
Wh_TR_21 | Check wether the add to cart option will work while click on them | 1.Open whitemart.in 2.Click refregerator 3.Click double door 4.Click side by side 5.Click red color | www.whitemart.in | It should add to cart and display a notification the item is added to cart | It doesnot give any notification | Fail
Wh_TR_22 | Check wether the buy now button will work while click on them | 1.Open whitemart.in 2.Click refregerator 3.Click double door 4.Click side by side 5.Click buy now | www.whitemart.in | It should go the purchasing page | It redirected to the purchasing page | Pass
Wh_TR_23 | Check wether the 8K icon will work while click on them | 1.Open whitemart.in 2.Click TV 3.Click 8K | www.whitemart.in | It should display the 8K tvs | It display a error message the products are out pf stock | Fail

## WASHING MACHINE AND HOME APPLIA
WHITE MART
VERSION NO:119.0.6045.160 (Official Build) (64-bit) |  |  |  | TESTED BY:Neenu Avarachan
VERFIED BY : RAKHI |  |  |  | DATE:24-FEBRUARY-2024
ENVIRONMENT DETAILS:OS-WINDOWS,BROWSER-CHROME |  |  |  | MODULE NAME:WASHING MACHINE AND HOME APPLIANCES
TEST ID | TEST DISCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
WM_WH_01 | Check wether the washing machine icon will work while click on them | 1.Open white mart.in 2.Click washing machine | www.whitemart.in | It should display the two catagories og whashing machine,semi automatic and fully automatic | It displayed two catagories of washing machine semi and fully automatic | Pass
WM_WH_02 | Check wether the semi automatic option will work while click on them | 1.Open white mart.in 2.Click washing machine 3.Semi automatic | www.whitemart.in | It should display the various semi automatic washing machine | It does not gives any semi automatic washing machine | Fail
WM_WH_03 | Check wether the top loading washing machine will work while click on them | 1.Open white mart.in 2.Click washing machine 3.Full automatic 4.Top loading | www.whitemart.in | It should display the various top loading washing machine | It does not give any information about washing machine,its stuck on that page | Fail
WM_WH_04 | Check wether the front loading washing machine while click on them | 1.Open white mart.in 2.Click washing machine 3.Full automatic 4.Front loading | www.whitemart.in | It should display various front loading washing machines | It does not give any information about washing machine,its stuck on that page | Fail
WM_WH_05 | Check wether the fully automatic link will work while click on them | 1.Open white mart.in 2.Click washing machine 3.Click Full automatic | www.whitemart.in | It should display various fully automatic machines | It does not gave any inofrmation about fully automatic machines,its stuck on that page. | Fail
WM_WH_06 | Check wether the home appliances icon will work while click on them | 1.Open white mart.in 2.Click home appliances | www.whitemart.in | It should display various home appliances | It displayed different kinds of home appliances | Pass
WM_WH_07 | Check wether the electric accessories icon will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click electric accessories | www.whitemart.in | It should display various electric accessories | It displayed a message the products are out of stock | Fail
WM_WH_08 | Check wether the air cooler icon will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click air cooler | www.whitemart.in | it should display different cooling options | It displayed different types of cooling options | Pass
WM_WH_09 | Check wether the category dropdown arrow will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click air cooler 4.Click category | www.whitemart.in | It should display differnet catagories of air cooler | It displayed diiferent catagories of air cooler | Pass
WM_WH_10 | Check wether the dropdown arrow of brand will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click air cooler 4.Click brand | www.whitemart.in | It should display differnet brands of air cooler | It displayed different brands of air cooler | Pass
WM_WH_11 | Check wether the dropdown arrow of wet grinders type will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click air cooler 4.Click wet grinders type | www.whitemart.in | It should display the different types of wet grinders | It displayed the cateories of wet grinders | Pass
WM_WH_12 | Check wether the table top checkbox will work while click on them | 1.Home appliances 2.Click home appliances 3.Click wet grinders type 4.Click table top | www.whitemart.in | It should select the check box and will display the details table top | It displayed a message the products are out of stock | Fail
WM_WH_13 | Check wether the drop down arrow cooker type will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click cooker type | www.whitemart.in | It should display the different catagories of cooker typt | It displayed different cataories of cooker type | Pass
WM_WH_14 | Check wether the add to compare icon will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click cooker type | www.whitemart.in | It should display the all item details in add to compare | It displayed all details in add to compare | Pass
WM_WH_15 | Check wether the add to compare icon will work more than 4 items | 1.Open white mart.in 2.Click home appliances 3.Click cooker type | www.whitemart.in | It should compare only four items and display error message the maximum products are already added to the list | It displayed an error message the maximum products are already added to the list. | Pass
WM_WH_16 | Check wether the clear all items icon will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click home appliances 4.Click fan | www.whitemart.in | It should clear all items from the list | It cleared all items from the list | Pass
WM_WH_17 | Check wether the color drop down arrow of fan will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click fan 4.Click color | www.whitemart.in | It should display red color fan | It displayed golden color fan | Fail
WM_WH_18 | Check wether the check box of all colors will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click fan 4.Click color | www.whitemart.in | It should display respective colorsof fan | It displayed the fans of respective colors | Pass
WM_WH_19 | Check wether the next button will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click fan 4.Click color | www.whitemart.in | It should move to the next page | It moved to the next page | Pass
WM_WH_20 | Check wether the prev button will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click fan 4.Click color | www.whitemart.in | It should move to the previous page | It moved to the previous page | Pass
WM_WH_21 | Check wether the warranty icon will work while click on them | 1.Open white mart.in 2.Click home appliances 3.Click fan 4.Click warranty | www.whitemart.in | It should display the details of warranty | It displayed the warraty details of respective items | pass
WM_WH_22 | check wether the manufacturing ,packaging and import icon will work while clcik on them | 1.Open white mart.in 2.Click home appliances 3.Click washing machine 4.Click manufacturing | www.whitemart.in | It should display the details of manufacturing,packaging and import dtails | It displayed a simple text country of manufacture,no any other details mentioned | Fail
WM_WH_23 | Check wether the view all plus icon will work while click on them | 1.Open wehitemart.in 2.Click home appliances 3.Click view all plus | www.whitemart.in | it should display different kinds of washing machines | It displayed different kinds of washing machines | Pass
WM_WH_24 | Check wether invertor ac icon of air conditioner will work while click on them | 1.Open whitemart.in 2.Click air conditioner 3.Click invertor Ac | www.whitemart.in | It should display different brands of invertor ac | It display a error message data fetch error | Fail
WM_WH_25 | Check wether Tower icon of air conditioner will work while click on them | 1.Open whitemart.in 2.Click air conditioner 3.Click Tower | www.whitemart.in | It should display different brands of tower | It display a error message data fetch error | Fail
WM_WH_26 | Check wether split ac icon of air conditioner will work while click on them | 1.Open whitemart.in 2.Click air conditioner 3.Click split ac | www.whitemart.in | It should display different brands of split ac | It display a error message data fetch error | Fail

## KITCHEN APPLIANCES
WHITE MART
VERSION NO:119.0.6045.160 (Official Build) (64-bit) |  |  |  | TESTED BY:NEENU AVARACHAN
VERFIED BY: RAKHI |  |  |  | DATE:24-FEBRUARY-2024
ENVIRONMENT DETAILS:OS-WINDOWS,BROWSER-CHROME |  |  |  | MODULE NAME: KITCHEN APPLIANCES
TEST ID | TEST DISCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
WM_KA_01 | Check wether the kitchen appliances icon will work while click on them | 1.Open white mart.in 2.Click kitchen appliances | www.white mart.in | It should display various kitchen products | It displayed various kitechen products | Pass
WM_KA_02 | Check wether the drop down arrow brand will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click Brand | www.white mart.in | It should display various brands of mixer | It displayed various brands of mixer | Pass
WM_KA_03 | Check wether the drop down arrow of discount will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click discount | www.white mart.in | It should display the discount rates | It displayed discount rates | Pass
WM_KA_04 | Check wether the bosch chekbox will work while clcik on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click brand 5.select bosch | www.white mart.in | it should display various mixer of bosch | It displayed various bosch mixers | Pass
WM_KA_05 | Check wether the check box of prrethi will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click brand 5.select preethi | www.white mart.in | it should display various mixer of preethi | It displayed various preethi mixers | Pass
WM_KA_06 | Check wether the check box of vidiem will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click brand 5.select vidiem | www.white mart.in | it should display various mixer of vidiem | It displayed various vidiemi mixers | Pass
WM_KA_07 | Check wether the check box of pigieon will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click brand 5.select pigieon | www.white mart.in | it should display various mixer of pigieon | It displayed various pigieon mixers | Pass
WM_KA_08 | Check wether the check box of Lg will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click brand 5.select Lg | www.white mart.in | it should display various mixer of Lg | It displayed various Lg mixers | Pass
WM_KA_09 | Check wether the warranty icon of mixer will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click brand 5.select Lg | www.white mart.in | It should display warrant details of mixer | It displayed warranty details of mixer | Pass
WM_KA_10 | Check wether the manufacturing,packaging,import icon of mixer will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click brand 5.select Lg | www.white mart.in | It should display the details of manufacturing,packaging and import details | it displayed a simple text country manufactuer | Fail
WM_KA_11 | Check wether the microwave icon will work while click on them | 1.open white mart.in 2.Click kitchen appliances 3.Click microwave oven | www.white mart.in | It should display different kinds of mirowave oven | It displayed different kinds of microwave oven | Pass
WM_KA_12 | Check wether the warrany icon will work while click on them | 1.open white mart.in 2.Click kitchen appliances 3.Click microwave oven | www.white mart.in | It should display the details of warranty | It displayed warranty details of microwave oven | Pass
WM_KA_13 | Check wether the water cooler icon will work while click on them | 1.open white mart.in 2.Click kitchen appliances 3.Click water cooler | www.white mart.in | it should display different water coolers | It displayed different kinds of water coolers | Pass
WM_KA_14 | Check wether the drop down arrow of brand will work while click on them | 1.open white mart.in 2.Click kitchen appliances 3.Click water cooler 4.Click brand | www.white mart.in | It should display the various brands | It displayed various brands of water cooler | Pass
WM_KA_15 | Chec wether the voltas check box will work while click on them | 1.open white mart.in 2.Click kitchen appliances 3.Click water cooler 4.Click brand 5.click voltas | www.white mart.in | It should display voltas water coolers | It displayed various water coolers | Pass
WM_KA_16 | Check wether the dish washer icon will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.click dish washer | www.white mart.in | it should display differnet kinds of dish washer | It does not reply anything | Fail
WM_KA_17 | Check wether the presuure cooker icon will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.click pressure cooker | www.white mart.in | It should display different kinds of pressure cooker | It displayed different kinds of pressure cooker | Pass
WM_KA_18 | Check wether the drop down arrow of cooker capacity | 1.Open white mart.in 2.Click kitchen appliances 3.click pressure cooker 4.Click cooker capacity | www.white mart.in | It should display different capacities fo cooker | it displayed different kinds of cooker | Pass
WM_KA_19 | Check wether the HOB icon will work while click o them | 1.Open white mart.in 2.Click HOB | www.white mart.in | It should display different HOB | It displayed differnet HOB | Pass
WM_KA_20 | Check wether the all new options if microwave oven | 1.Open white mart.in 2.Click all knew microwave oven | www.white mart.in | It should dsplay latest mivrowave ovenl | It dispalyed different microwave oven | Pass
WM_KA_21 | Check wether the waranty icon of microwave will work while click ont them | 1.Open white mart.in 2.Click warranty | www.white mart.in | It should display the details warranty | It displayed the details of warrranty | pass
WM_KA_22 | check wether the mixer grinder icon will work while click on them | 1.Open white mart.in 2.Click mixer grinder | www.white mart.in | It should display various mixer grinder | It does not reply anything | Fail
WM_KA_23 | Check wether the microwave ovens manufacturing,packaging and import info icon will work while click on them | 1.Open white mart.in 2.Click microwave oven 3.Click manufacturing,pakaeging,import info | www.white mart.in | It should display the details of manufacturing.packaging and import details | It display only country manufactuer message | Fail
WM_KA_24 | Check wether the technical specification icon mixer grinder will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click mixer grinder 4.Click technical specification | www.white mart.in | It should display the various technical specification details of mixer grinder | It displayed technical specification of mixer grinder | Pass
WM_KA_25 | Check wether the general icon of mixer grinde will work while click on them | 1.Open white mart.in 2.Click kitchen appliances 3.Click mixer grinder 4.Click general | www.white mart.in | It should display the color ,brand and type of the mixer grinder | It displayed the color,brand and type of the mixer grinder | Pass

## BUG REPORT
WHITE MART.IN
ENVIRONMENT DETAILS : OS-WINDOWS,BROWSER-CHROME |  |  |  |  | DATE : 24-FEBRUARY-2024
VERIFIED BY : RAKHI |  |  |  |  | TESTED BY : NEENU AVARACHAN
Test Id | Bug Id | Expected Result | Bug Discription | Steps to Reproduce | Screenshot | Severity | Priority | Status
Wh_Home_36 | Def_Wm_01 | Telephone link will work properly while click on them | Telephone link is not working when its clicked | 1.www.whitemart.in 2.Click Telephone link |  | Minor | P3 | New
Wh_Home_37 | Def_Wm_02 | Mobile number link will work properly while click on them | Mobile number link is not working when its clicked | 1.www.whitemart.in 2.Click Mobile phone link |  | Minor | P3 | New
Wh_Home_39 | Def_Wm_03 | Franchese login icon will log in to franchese page while click on them | Its displayed a page not found error message when its ckicked | 1.www.whitemart.in 2.Click franchese login |  | Major | P2 | New
Wh_Home_41 | Def_Wm_04 | Will give a notification message while its subscirbed | Its does not gives any notifiction whether its subsciribed or not | 1.www.whitemart.in 2.Click subscribe |  | Minor | P3 | New
Wh_Home_42 | Def_Wm_05 | Will give a notification message when we enter an invalid mail id | It doesnot gave any notification message wether we enter an in valid emailid | 1.www.whitemart.in 2.Click subscribe |  | Minor | P3 | New
Wh_TR_14 | Def_Wm_06 | Single door refrigerator icon will display the single door refrigerators while click on them instead of showing the products are out of stock | It display a message the products are out of stock | 1.www.whitemart.in 2.Click Single door |  | Major | P2 | New
Wh_TR_18 | Def_Wm_07 | Bottom freezor refrigerator icon will display the bottom freezor refrigerators while click on them instead of showing the products are out of stock | It display a message the products are out of stock | 1.www.whitemart.in 2.Click bottom freeezor |  | Major | P2 | New
Wh_TR_15 | Def_Wm_08 | Double door refrigerator icon will display the double door refrigerators while click on them instead of showing the products are out of stock | It display a message the products are out of stock | 1.www.whitemart.in 2.Click double door |  | Major | P2 | New
Wh_TR_17 | Def_Wm_09 | Multi door refrigerator icon will display the multi door refrigerators while click on them instead of showing the products are out of stock | It display a message the products are out of stock | 1.www.whitemart.in 2.Click multi door |  | Major | P2 | New
Wh_TR_20 | Def_Wm_10 | Red color check box will display red color refrigerators when its selected | Its displayed black color refrigerators | 1.www.whitemart.in 2.Click multi door 3.Select red color |  | Major | P2 | New
Wh_TR_21 | Def_Wm_11 | It should be good to display a notification message wether we click add to cart | It does not display any notification | 1.www.white mart.in |  | Enhancement | P3 | New
WM_WH_02 | Def_Wm_12 | Semi automatic icon will display semi automatic washing machines | It does not display any semi automatic washing machines | 1.www.white mart.in 2.Click washing machine |  | Major | P2 | New
WM_WH_03 | Def_Wm_13 | It will display different brands of top loading washing machine while click on the top loading icon | It does not give any information about top loading washing machine,its stuck on that page | 1.Open white mart.in 2.Click washing machine 3.Full automatic 4.Top loading |  | Major | P2 | New
WM_WH_04 | Def_Wm_14 | It will display different brands of front loading washing machine while click on the top loading icon | It does not give any information about front loading washing machine,its stuck on that page | 1.Open white mart.in 2.Click washing machine 3.Full automatic 4.front loading |  | Major | P2 | New
WM_WH_05 | Def_Wm_15 | It should display all types of fully automatic machine while click on the fully automatic icon | It does not gave any inofrmation about fully automatic machines,its stuck on that page. | 1.Open white mart.in 2.Click washing machine 3.Full automatic |  | Major | P2 | New
WM_WH_07 | Def_Wm_16 | It should display various electric accessories while click on the electric accessories icon | It displayed a message the products are out of stock | 1.Open white mart.in 2.Click home appliances 3.Click electric accessories |  | Major | P2 | New
WM_WH_12 | Def_Wm_17 | It should select the check box and will display the details table top | It displayed a message the products are out of stock | 1.Home appliances 2.Click home appliances 3.Click wet grinders type 4.Click table top |  | Major | P2 | New
WM_WH_17 | Def_Wm_18 | It should display red color fan while select on the red color check box | It displayed golden color fan | 1.Open white mart.in 2.Click home appliances 3.Click fan 4.Click color |  | Trivial | P3 | New
WM_WH_22 | Def_Wm_19 | It should display the details of manufacturing,packaging and import details while click on the icon | It displayed a simple text country of manufacture,no any other details mentioned | 1.Open white mart.in 2.Click home appliances 3.Click washing machine 4.Click manufacturing |  | Minor | P3 | New
WM_KA_22 | Def_Wm_20 | It should display various mixer grinder while click on the icon | It does not reply anything | 1.Open white mart.in 2.Click mixer grinder |  | Major | P2 | New
WM_KA_23 | Def_Wm_21 | It should display the details of manufacturing.packaging and import details while click on the icon | It display a message only country manufactuer | 1.Open white mart.in 2.Click microwave oven 3.Click manufacturing,pakaeging,import info |  | Minor | P3 | New
Wh_Home_53 | Def_Wm_22 | It should display a error message the email id is invalid while enter an invalid email id | It directly goes to the home page | 1.Open white mart.in 2.Click log in |  | Major | P2 | New
Wh_Home_54 | Def_Wm_23 | It should display an error message wether we create account using an invalid email id | It directly go to page user | 1.Open white mart.in 2.Create account |  | Major | P2 | New
Wh_Home_60 | Def_Wm_24 | It should display a error message the email id is invalid while we enter an invalid email id | It accepted the email id | 1.Open whitemart.in 2.Click log in 3.Click forgot password |  | Major | P2 | New
Wh_Home_64 | Def_Wm_25 | It should display a error message the pincode is invalid while we enter an invalid pincode | It accepted the pincode | 1.Open whitemart.in 2.Click deliver to icon 3.Click enter pincode |  | Major | P2 | New
Wh_TR_23 | Def_Wm_26 | It should display 8K tvs while click on them | It display a message the products are out of stock | 1.Open whitemart.in 2.Click TV 3.Click 8K |  | Major | P2 | New
WM_WH_24 | Def_Wm_27 | It should display different brands of invertor ac while clcik on them | It displays data fetch error | 1.Open whitemart.in 2.Click air conditioner 3.Click Inverto Ac |  | Major | P2 | New
WM_WH_25 | Def_Wm_28 | It should display different brands of tower while clcik on them | It displays data fetch error | 1.Open whitemart.in 2.Click air conditioner 3.Click tower |  | Major | P2 | New
WM_WH_26 | Def_Wm_29 | It should display different brands of split ac while clcik on them | It displays a error message the products are out of stock | 1.Open whitemart.in 2.Click air conditioner 3.Click Split ac |  | Major | P2 | New
WM_KA_10 | Def_Wm_30 | It should display the detaile of manufacturing and packaging while click on the manufacturing and packaging info | Its display a text just country manufactuer | 1.Open white mart.in 2.Click kitchen appliances 3.Click Mixer 4.Click brand 5.select Lg |  | Minor | P3 | New
WM_KA_16 | Def_Wm_31 | It should display different types of dish washer while click on them | Its does not reply anything,stuck on that page | 1.Open white mart.in 2.Click kitchen appliances 3.click dish washer |  | Major | P2 | New

## DEFECT DISTRIBUTION GRAPH
DEFECT DISTRIBUTION GRAPH
MODULE NAME | DEFECT DISTRIBUTION
CREATE ACCOUNT AND HOME PAGE | 9
TV AND REFRIGERATOR | 7
WASHING MACHINE AND HOME APPLIANCES | 11
KITCHEN APPLIANCES | 4

## TEST REPORT
SL NO | MODULE NAME | TESTCASE PASSED | TESTCASE FAILED | TOTAL TESTCASE
1 | CREATE ACCOUNT AND HOME PAGE | 55 | 9 | 64
2 | TV AND REFRIGERATOR | 16 | 7 | 23
3 | WASHING MACHINE AND HOME APPLIANCES | 15 | 11 | 26
4 | KITCHEN APPLIANCES | 21 | 4 | 25